## Slide 1: Dragon Mine Preliminary Assessment, Site Investigation & Remediation Proposal Bureau of Land Management. Ground Guardians LLC.
Bowie Ching, Andres Garcia Rico, Zack Kauranen, Jorja Whitcher,
CENE 476
(12/06/2024)
1

## Slide 2
Purpose:
  Preliminary Assessment and Site Investigation to assess health risks and propose remedial action
Client:
  Eric Zielske from the Bureau of Land Management
Background:
  Active from 1800s to 1942 produced vanadinite, gold, and silver
Introduction
2
Figure 1: Arizona Location Map [1]

## Slide 3
Figure 2: County Location Map [2]
Location Map
3
Notes: MAKE WICKENBURG MORE CLEAR

## Slide 4
Figure 3: Vicinity Map [3]
Vicinity Map
4
Notes: MAKE WICKENBURG MORE CLEAR

## Slide 5
Legend
Soil | Antimony | Arsenic | Lead | Molybdenum | Vanadium
Area of Concern | (mg/kg) |  |  |  | 
Downgradient Debris | <394 | 5 | 16 | <29 | 259
Mill Foundation | <437 | 10 | 115 | <34 | 368
Water Troughs | <199 | 15 | 101 | 27 | <56
Waste Pile | <368 | <28 | 667 | <28 | 548
Foundation | <579 | 29 | 593 | 12 | 515
Conveyor Foundation | <447 | 26 | 373 | <35 | 409
Heap Leach? | <396 | <24 | 414 | <30 | 378
Heap Leach? | <405 | 9 | 141 | <31 | 295
Heap Leach? | <385 | <36 | 1062 | 17 | 455
Heap Leach? | 43 | <33 | 827 | 5 | 538
Waste Rock Pile | <381 | <18 | 228 | <29 | 1241
Waste Rock Pile | <390 | <14 | 127 | <31 | 347
Mill Platform | <334 | <60 | 3967 | 88 | 581
Red Tailings | <324 | <65 | 4894 | 102 | 440
Red Tailings near collapsed structure | <226 | <83 | 10776 | 485 | 594
Tailings near mill | <438 | <38 | 862 | <35 | 288
Background | <410 | 7 | 91 | <32 | 369
Background | <380 | 5 | 49 | <30 | 432
Background | <371 | 10 | 42 | <29 | 371
Background | <426 | 7 | 57 | <33 | 335
Background | <375 | 5 | 21 | <29 | 323
Table 1: Contaminants of Concern ECM Site Investigation 2019 [4]
5
= Above AZ Non-residential Soil Remediation Levels
= Above AZ Residential Soil Remediation Levels
= Above AZ Ecological Soil Remediation Levels

## Slide 6
Figure 4: Project map [5]
Project Map
6

## Slide 7
Task 1.1: Sampling and Analysis Plan
Task 1.2: Health and Safety Plan
Task 1.3: Lab Binder/Lab Access
Task 2: Site Investigation
Task 1: Work Plan
7
Figure 5: Soil Collection [6]

## Slide 8
Task 3.1: Sample Drying
Task 3.2: Sample Sieving
Task 3.3: X-Ray Fluorescence (XRF) Testing
Task 3.4: Acid Digestion
Task 3.5: Flame Atomic Absorption (FAA) / Inductively Coupled Plasma (ICP)
Task 4.1: Identification of Human Health and Ecological Contaminants of Concern (COCs)
Task 4.2: Identify Exposure Point Concentrations for all COCs
Task 4.3: XRF in-situ vs ex-situ Analysis
Task 4.4: XRF ex-situ vs FAA/ICP Analysis
Task 4.5: Quality Assurance & Quality Control Analysis
Task 4: Data Analysis
Task 3: Laboratory Analysis
8

## Slide 9
Task 5.1: Maps of Contaminant Distribution
Task 5.2: Migration Pathways
Task 5.3: Conceptual Site Model (CSM)
Task 6.1: Toxicity Assessment
Task 6.2: Exposure Assessment
Task 6.3: Risk Characterization
Task 6: Human Health Risk Assessment
Task 5: Contaminant Pathways
9

## Slide 10
Task 7.1: Identification of Potentially at-risk Species
Task 7.2: Identification of Area Use Factors
Task 7.3: Determination of Ecological Risk
Task 8.1: Remedial Action Objectives
Task 8.2: Develop Alternatives
Task 8.3: Evaluate Alternatives and Select Preferred Alternative
Task 8.4: Design of Preferred Alternative
Task 8: Remedial Actions
Task 7: Ecological Risk Assessment
10

## Slide 11
Task 10.1: 30% Report
Task 10.2: 60% Report
Task 10.3: 90% Report
Task 10.4: Final Report
Task 10: Project Deliverables
Task 9: Project Impacts
Task 11.1: Meetings
Task 11.2: Schedule Management
Task 11.3: Resource Management
Task 11: Project Management
11

## Slide 12
Water Sampling/Analysis
Air Sampling/Analysis
Exclusions
12

## Slide 13
13
Figure 6: Project Gantt Chart

## Slide 14
‌Senior Engineer
  Master’s Degree
  Professional Engineer
  15+ years of experience
  Project Manager
Engineer
  Bachelor’s Degree
  Engineer-In-Training
  ~3 years of experience
  Performs majority of project work
Lab Technician
  Performs all laboratory work with supervision of Engineer
  Present during Site Investigation
Staffing
14

## Slide 15
Task | Senior Engineer | Engineer | Lab Technician | Task Total
Task 1.0 Work Plan |  |  |  | 
Task 1.1 Sampling and Analysis Plan | 5 | 30 | 0 | 35
Task 1.2 Health and Safety Plan | 5 | 15 | 0 | 20
Task 1.3 Lab Binder | 0 | 5 | 15 | 20
Task 2.0 Site Investigation | 25 | 50 | 50 | 125
Task 3.0 Laboratory Analysis |  |  |  | 
Task 3.1 Sample Drying | 0 | 2 | 50 | 52
Task 3.2 Sample Sieving | 0 | 2 | 60 | 62
Task 3.3 XRF Testing | 0 | 2 | 60 | 62
Task 3.4 Acid Digestion | 0 | 1 | 1 | 2
Task 3.5 FAA/ICP | 0 | 1 | 1 | 2
Task 4.0 Data Analysis |  |  |  | 
Task 4.1 Identification of Human Health and Ecological COCs | 2 | 5 | 0 | 7
Task 4.2 Identification of EPCs for all COCs | 2 | 15 | 0 | 17
Task 4.3 XRF In-situ vs Ex-situ analysis | 0 | 10 | 0 | 10
Task 4.4 XRF Ex-Situ vs FAA/ICP analysis | 0 | 10 | 0 | 10
Task 4.5 QA/QC analysis | 2 | 10 | 5 | 17
Task 5.0 Contaminant Pathways |  |  |  | 
Task 5.1 Maps of Contaminant Distribution | 2 | 15 | 0 | 17
Task 5.2 Migration Pathways | 0 | 2 | 0 | 2
Task 5.3 Conceptual Site Model (CSM) | 2 | 4 | 0 | 6
Task 6.0 Human Health Risk Assessment |  |  |  | 
Task 6.1 Toxicity Assessment | 0 | 8 | 0 | 8
Task 6.2 Exposure Assessment | 0 | 20 | 0 | 20
Task 6.3 Risk Characterization | 2 | 10 | 0 | 12
Task 7.0 Ecological Risk Assessment |  |  |  | 
Task 7.1 Identification of Potentially at-risk Species | 2 | 15 | 0 | 17
Task 7.2 Identification of Area Use Factors | 2 | 15 | 0 | 17
Task 7.3 Determination of Ecological Risk | 2 | 10 | 0 | 12
Task 8.0 Remedial Actions |  |  |  | 
Task 8.1 Remedial Action Objectives | 2 | 6 | 0 | 8
Task 8.2 Develop Alternatives | 5 | 15 | 0 | 20
Task 8.3 Evaluate Alternatives and Select Preferred Alternative | 1 | 5 | 0 | 6
Task 8.4 Design of Preferred Alternative | 5 | 20 | 0 | 25
Task 9.0 Project Impacts | 1 | 3 | 0 | 4
Task 10.0 Project Deliverables |  |  |  | 
Task 10.1 30% | 2 | 8 | 0 | 10
Task 10.2 60% | 2 | 8 | 0 | 10
Task 10.3 90% | 2 | 8 | 0 | 10
Task 10.4 Final | 2 | 8 | 0 | 10
Task 11.0 Project Management |  |  |  | 
Task 11.1 Meetings | 30 | 60 | 30 | 120
Task 11.2 Schedule Management | 10 | 5 | 0 | 15
Task 11.3 Resource Management | 2 | 2 | 0 | 4
Subtotal Hours | 117 | 405 | 272 | 
Total Hours | 794 |  |  | 
Staffing
15

## Slide 16
Project Costs Summary |  |  |  |  | 
Subsection | Classification | Qty | Rate | Unit | Cost
Personnel | Senior Engineer | 117 | $300 | $/hr | $35,100
 | Engineer | 405 | $135 | $/hr | $54,675
 | Lab Technician | 272 | $35 | $/hr | $9,520
 | Total Personnel |  |  |  | $99,295
Travel | NAU Mileage Rate | 300 | $0.40 | $/mile | $120
 | Rental: NAU Suburban | 2 | $65 | $/day | $130
 | Hotel 1 Night | 5 | $100 | $/room | $500
 | PerDiem; 5 persons | 2 days | $30 | $/day-person | $300
 | Total Travel |  |  |  | $1,050
Supplies | Ziplock Gallon Freezer Bags, 120 ct | 1 | $16 | $/pack | $16
 | Trowel | 8 | $10 | EA | $80
 | Rental: 2 GPS devices | 2 days | $120 | $/device-day | $480
 | Soap | 1 | $6 | $/bottle | $6
 | Marker Flags, 50 pack | 2 | $7 | $/pack | $14
 | Plastic Bins, 2 pack | 2 | $57 | $/pack | $114
 | 5 gal Buckets | 4 | $7 | EA | $28
 | Water, 12 pack | 2 | $4 | $/pack | $8
 | Paper Towels, 2 pack | 1 | $7 | $/pack | $7
 | Sharpie, 5 pack | 1 | $5 | $/pack | $5
 | Nitrile Gloves, 1000 pack | 1 | $45 | $/pack | $45
 | Trash Bags, 74 pack | 1 | $20 | $/pack | $20
 | Clipboards, 6 pack | 1 | $12 | $/pack | $12
 | Logbooks | 2 | $5 | EA | $10
 | Measuring Tapes | 4 | $20 | EA | $80
 | Scrub Brushes | 4 | $3 | EA | $12
 | Rental: NAU Soils Lab | 20 | $100 | $/day | $2,000
 | Rental: XRF Device | 10 | $300 | $/day | $3,000
 | Total Supplies |  |  |  | $5,937
Subcontract | Western Technologies | 10 | $100 | $/sample | $1,000
Total Cost |  |  |  |  | $107,282
Personnel = $99,295
Travel = $1,050
Supplies = $5,937
Total = $107,282
Cost of Engineering Services
16

## Slide 17: References
‌
[1] J. Whitcher, "Dragon Mine: Preliminary Assessment Location Map," AUTOCAD, 2024.
[2] A G. Rico, "Dragon Mine: Preliminary Assessment Location Map," AUTOCAD, 2024.
[3] A. G. Rico, Google Earth , 2024.
[4] ECM Consultants, "Site Summary Report for the Dragon Mine," ECM Consultants, 2020.
[5] G. G. LLC, "Dragon Mine: Preliminary Assessment Project Map," AUTOCAD, 2024.
[6] “Redevelopment Site Assessments,” Environmental Site Assessment and Environmental Due Diligence, Aug. 29,
2024. https://www.aeasinc.com/redevelopment
17

## Slide 18
QUESTIONS?
18