## Week 3
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | NL | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey
1.2 I can navigate the web application from the home page
2. User Account Creation | 2.1 I can sign up, sign in, and sign out
2.2 I can edit my profile
2.3 I can view my profile
2.4 My profile contains all necessary information
2.4.1 Age
2.4.2 Level of Education
2.4.3 Balance (USD)
2.4.3.1 Balance should not be editable by the user
2.4.4 Years of Professional Experience
2.4.5 Occupation
Communication Memo
Software Design Document Draft | bar: 2022-01-24 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment | bar: 2022-02-07 to 2022-02-14
6.6.1 Documentation | bar: 2022-02-07 to 2022-02-14
Design Review II Presentation | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Software Testing Plan | bar: 2022-03-21 to 2022-03-28
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final | bar: 2022-04-11 to 2022-04-18
Completed Team Website | bar: 2022-04-11 to 2022-04-18
Capstone Poster | bar: 2022-04-11 to 2022-04-18
Capstone Presentation + Dry-run | bar: 2022-04-11 to 2022-04-18
Peer Evaluation #4 | bar: 2022-04-18
Final Product Acceptance Demo | bar: 2022-04-18 to 2022-04-25
Project Completion Work | bar: 2022-04-25 to 2022-05-02
Final (as-built) Report | bar: 2022-04-25 to 2022-05-02
Team Reflection Document | bar: 2022-04-25 to 2022-05-02
Final Project Delivery | bar: 2022-05-02
Peer Evaluation #5 | bar: 2022-05-02
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 4
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | NL | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey
1.2 I can navigate the web application from the home page
2. User Account Creation | 2.1 I can sign up, sign in, and sign out
2.2 I can edit my profile
2.3 I can view my profile
2.4 My profile contains all necessary information
2.4.1 Age
2.4.2 Level of Education
2.4.3 Balance (USD)
2.4.3.1 Balance should not be editable by the user
2.4.4 Years of Professional Experience
2.4.5 Occupation
Communication Memo
Software Design Document Draft | bar: 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment | bar: 2022-02-07 to 2022-02-14
6.6.1 Documentation | bar: 2022-02-07 to 2022-02-14
Design Review II Presentation | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Software Testing Plan | bar: 2022-03-21 to 2022-03-28
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final | bar: 2022-04-11 to 2022-04-18
Completed Team Website | bar: 2022-04-11 to 2022-04-18
Capstone Poster | bar: 2022-04-11 to 2022-04-18
Capstone Presentation + Dry-run | bar: 2022-04-11 to 2022-04-18
Peer Evaluation #4 | bar: 2022-04-18
Final Product Acceptance Demo | bar: 2022-04-18 to 2022-04-25
Project Completion Work | bar: 2022-04-25 to 2022-05-02
Final (as-built) Report | bar: 2022-04-25 to 2022-05-02
Team Reflection Document | bar: 2022-04-25 to 2022-05-02
Final Project Delivery | bar: 2022-05-02
Peer Evaluation #5 | bar: 2022-05-02
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 5
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | NL | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey
1.2 I can navigate the web application from the home page
2. User Account Creation | 2.1 I can sign up, sign in, and sign out
2.2 I can edit my profile
2.3 I can view my profile
2.4 My profile contains all necessary information
2.4.1 Age
2.4.2 Level of Education
2.4.3 Balance (USD)
2.4.3.1 Balance should not be editable by the user
2.4.4 Years of Professional Experience
2.4.5 Occupation
Communication Memo
Software Design Document Draft
3. Study Creation | 3.1 When logged in, I can create a study
3.2 I can view a study I previously created
3.2.1 A public landing page for every study on the site. accessible by unique URL
3.3 I can edit a study I previously created
3.4 The study contains a title and description
3.5 The study contains a creation date and expiry date
3.6 The study contains a list of enrolled accounts
3.7 The study contains enrollment criteria
3.8 Valid participants can enroll in the study
3.9 Invalid participants cannot enroll in the study
3.10 The study contains a balance (USD)
3.11 The study contains a payout amount (USD)
3.12 The study contains a completion code and external survey link
Software Design Document Final | bar: 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it
5.2 The study adds users to this list when they enter the completion code
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment | bar: 2022-02-07 to 2022-02-14
6.6.1 Documentation | bar: 2022-02-07 to 2022-02-14
Design Review II Presentation | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Software Testing Plan | bar: 2022-03-21 to 2022-03-28
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final | bar: 2022-04-11 to 2022-04-18
Completed Team Website | bar: 2022-04-11 to 2022-04-18
Capstone Poster | bar: 2022-04-11 to 2022-04-18
Capstone Presentation + Dry-run | bar: 2022-04-11 to 2022-04-18
Peer Evaluation #4 | bar: 2022-04-18
Final Product Acceptance Demo | bar: 2022-04-18 to 2022-04-25
Project Completion Work | bar: 2022-04-25 to 2022-05-02
Final (as-built) Report | bar: 2022-04-25 to 2022-05-02
Team Reflection Document | bar: 2022-04-25 to 2022-05-02
Final Project Delivery | bar: 2022-05-02
Peer Evaluation #5 | bar: 2022-05-02
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 6
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | NL | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey
1.2 I can navigate the web application from the home page
2. User Account Creation | 2.1 I can sign up, sign in, and sign out
2.2 I can edit my profile
2.3 I can view my profile
2.4 My profile contains all necessary information
2.4.1 Age
2.4.2 Level of Education
2.4.3 Balance (USD)
2.4.3.1 Balance should not be editable by the user
2.4.4 Years of Professional Experience
2.4.5 Occupation
Communication Memo
Software Design Document Draft
3. Study Creation | 3.1 When logged in, I can create a study
3.2 I can view a study I previously created
3.2.1 A public landing page for every study on the site. accessible by unique URL
3.3 I can edit a study I previously created
3.4 The study contains a title and description
3.5 The study contains a creation date and expiry date
3.6 The study contains a list of enrolled accounts
3.7 The study contains enrollment criteria
3.8 Valid participants can enroll in the study
3.9 Invalid participants cannot enroll in the study
3.10 The study contains a balance (USD)
3.11 The study contains a payout amount (USD)
3.12 The study contains a completion code and external survey link
Software Design Document Final
Peer Evaluation #1
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it
5.2 The study adds users to this list when they enter the completion code
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-14
6.6 I can create a working admin account upon deployment | bar: 2022-02-28 to 2022-03-07
6.6.1 Documentation | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. Overflow | 8.1 Change profile age to a birthdate as a proper date field. | bar: 2022-02-28 to 2022-03-07
8.2 Customizable expiration date to studies | bar: 2022-02-28 to 2022-03-07
8.3 Bootstrap for better UX | bar: 2022-02-28 to 2022-03-07
8.3.1 custom elements and color schemes | bar: 2022-02-28 to 2022-03-07
8.4 More enrollment criteria per client request | bar: 2022-02-28 to 2022-03-07
8.4.1 criteria for countries (origin and current location) | bar: 2022-02-28 to 2022-03-07
8.5 improve initial log-in flow for github auth + email verification | bar: 2022-02-28 to 2022-03-07
8.6 Disable auth if api info not defined in .env | bar: 2022-02-28 to 2022-03-07
8.7 Reorganize code into apps? Researcher code in researchers/ etc. | bar: 2022-02-28 to 2022-03-07
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final | bar: 2022-04-11 to 2022-04-18
Completed Team Website | bar: 2022-04-11 to 2022-04-18
Capstone Poster | bar: 2022-04-11 to 2022-04-18
Capstone Presentation + Dry-run | bar: 2022-04-11 to 2022-04-18
Peer Evaluation #4 | bar: 2022-04-18
Final Product Acceptance Demo | bar: 2022-04-18 to 2022-04-25
Project Completion Work | bar: 2022-04-25 to 2022-05-02
Final (as-built) Report | bar: 2022-04-25 to 2022-05-02
Team Reflection Document | bar: 2022-04-25 to 2022-05-02
Final Project Delivery | bar: 2022-05-02
Peer Evaluation #5 | bar: 2022-05-02
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 7
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | NL | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey
1.2 I can navigate the web application from the home page
2. User Account Creation | 2.1 I can sign up, sign in, and sign out
2.2 I can edit my profile
2.3 I can view my profile
2.4 My profile contains all necessary information
2.4.1 Age
2.4.2 Level of Education
2.4.3 Balance (USD)
2.4.3.1 Balance should not be editable by the user
2.4.4 Years of Professional Experience
2.4.5 Occupation
Communication Memo
Software Design Document Draft
3. Study Creation | 3.1 When logged in, I can create a study
3.2 I can view a study I previously created
3.2.1 A public landing page for every study on the site. accessible by unique URL
3.3 I can edit a study I previously created
3.4 The study contains a title and description
3.5 The study contains a creation date and expiry date
3.6 The study contains a list of enrolled accounts
3.7 The study contains enrollment criteria
3.8 Valid participants can enroll in the study
3.9 Invalid participants cannot enroll in the study
3.10 The study contains a balance (USD)
3.11 The study contains a payout amount (USD)
3.12 The study contains a completion code and external survey link
Software Design Document Final
Peer Evaluation #1
4. Study Discovery | 4.1 I can see a web page with a list of Studies
4.1.1 The web page only shows me Studies for which I am eligible for enrollment
4.1.2 The web page only shows me Studies which have not expired
4.2 I can click on a Study to go to its landing page
4.3 I can receive email notifications when a Study is created
4.3.1 I only receive study notifications if I'm eligible for the study
5. Study Completion | 5.1 The study contains a list of accounts who have completed it
5.2 The study adds users to this list when they enter the completion code
UGRADS Registration | bar: 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu
6.2 I can edit Accounts and Profiles from the admin menu
6.3 I can view Studies from the admin menu
6.4 I can edit Studies from the admin menu
6.5 I can log into the admin menu with a secure password
6.6 I can create a working admin account upon deployment | bar: 2022-02-28 to 2022-03-07
6.6.1 Documentation | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field. | bar: 2022-05-02
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH) | bar: 2022-05-02
9.3 Bootstrap for better UX | bar: 2022-05-02
9.3.1 custom elements and color schemes | bar: 2022-05-02
9.4 More enrollment criteria per client request | bar: 2022-05-02
9.4.1 criteria for countries (origin and current location) | bar: 2022-05-02
9.5 improve initial log-in flow for github auth + email verification | bar: 2022-05-02
9.6 Disable auth if api info not defined in .env | bar: 2022-05-02
9.7 Reorganize code into apps? Researcher code in researchers/ etc. | bar: 2022-05-02
9.7.1 study app | bar: 2022-05-02
9.7.2 payments app | bar: 2022-05-02
9.7.3 research app | bar: 2022-05-02
9.7.4 participate app | bar: 2022-05-02
9.7.5 profile app | bar: 2022-05-02
9.8 Check if user is authenticated through GitHub | bar: 2022-05-02
9.9 Display GitHub avatar if user is authenticated through GitHub | bar: 2022-05-02
9.10 Add GitHub enrollment criteria | bar: 2022-05-02
9.10.1 Add GitHub account age | bar: 2022-05-02
9.11 Move study_email_helper to a custom signal that fires upon study creation | bar: 2022-05-02
9.12 I can’t see other email recipients in the group email for study notifications NOTE: currently all email recipients are in the “to” field. Maybe we should send individual emails instead of a batch email | bar: 2022-05-02
9.13 Email notifications are parallelized NOTE: currently this blocks an http response upon study creation | bar: 2022-05-02
9.14 Claims are parallelized NOTE: currently this blocks on two different api calls to PayPal | bar: 2022-05-02
9.15 Fix the warning about naive datetime upon study creation | bar: 2022-05-02
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final | bar: 2022-04-11 to 2022-04-18
Completed Team Website | bar: 2022-04-11 to 2022-04-18
Capstone Poster | bar: 2022-04-11 to 2022-04-18
Capstone Presentation + Dry-run | bar: 2022-04-11 to 2022-04-18
Peer Evaluation #4 | bar: 2022-04-18
Final Product Acceptance Demo | bar: 2022-04-18 to 2022-04-25
Project Completion Work | bar: 2022-04-25 to 2022-05-02
Final (as-built) Report | bar: 2022-04-25 to 2022-05-02
Team Reflection Document | bar: 2022-04-25 to 2022-05-02
Final Project Delivery | bar: 2022-05-02
Peer Evaluation #5 | bar: 2022-05-02
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 8
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | NL | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21
7.2 I can fund my geeksurvey account | bar: 2022-02-21
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21
8. CRUNCH | 8.1 I can delete studies
8.2 I can customize my study’s expiration date
8.3 I can set a maximum number of participants in a study
8.3.1 Participants cannot enroll when the maximum is reached
8.4 I can remove participants who are enrolled in my study
8.5 I can approve or deny compensation for participants who completed my study
8.6 I can opt in or out of email notifications (opt out by default)
Design Review II Presentation Step 2
Alpha Prototype Demo
Peer Evaluation #2
Design Review II Presentation Step 3
Design Review III Presentation
Peer Evaluation #3
Project Mini-Video Final
Completed Team Website
Capstone Poster
Capstone Presentation + Dry-run
Peer Evaluation #4
Final Product Acceptance Demo
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 criteria for countries (origin and current location)
9.5 improve initial log-in flow for github auth + email verification
9.6 Disable auth if api info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 study app
9.7.2 payments app
9.7.3 research app
9.7.4 participate app
9.7.5 profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: currently all email recipients are in the “to” field. Maybe we should send individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: currently this blocks on two different api calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 9
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | NL | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-02-28
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-02-28
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-02-28
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-02-28
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-02-28
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-02-28
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28
8.2 I can customize my study’s expiration date | bar: 2022-02-28
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28
Design Review II Presentation Step 2 | bar: 2022-02-28
Alpha Prototype Demo | bar: 2022-02-28
Peer Evaluation #2
Design Review II Presentation Step 3
Design Review III Presentation
Peer Evaluation #3
Project Mini-Video Final
Completed Team Website
Capstone Poster
Capstone Presentation + Dry-run
Peer Evaluation #4
Final Product Acceptance Demo
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 criteria for countries (origin and current location)
9.5 improve initial log-in flow for github auth + email verification
9.6 Disable auth if api info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 study app
9.7.2 payments app
9.7.3 research app
9.7.4 participate app
9.7.5 profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: currently all email recipients are in the “to” field. Maybe we should send individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: currently this blocks on two different api calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 10 (Spring Break)
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | NL | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation Step 2 | bar: 2022-02-28 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Design Review II Presentation Step 3
Design Review III Presentation
Peer Evaluation #3
Project Mini-Video Final
Completed Team Website
Capstone Poster
Capstone Presentation + Dry-run
Peer Evaluation #4
Final Product Acceptance Demo
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 criteria for countries (origin and current location)
9.5 improve initial log-in flow for github auth + email verification
9.6 Disable auth if api info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 study app
9.7.2 payments app
9.7.3 research app
9.7.4 participate app
9.7.5 profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: currently all email recipients are in the “to” field. Maybe we should send individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: currently this blocks on two different api calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 11
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | NL | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation Step 2 | bar: 2022-02-28 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Design Review II Presentation Step 3 | bar: 2022-03-14
Software Testing Plan
Design Review III Presentation
Peer Evaluation #3
Project Mini-Video Final
Completed Team Website
Capstone Poster
Capstone Presentation + Dry-run
Peer Evaluation #4
Final Product Acceptance Demo
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 criteria for countries (origin and current location)
9.5 improve initial log-in flow for github auth + email verification
9.6 Disable auth if api info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 study app
9.7.2 payments app
9.7.3 research app
9.7.4 participate app
9.7.5 profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: currently all email recipients are in the “to” field. Maybe we should send individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: currently this blocks on two different api calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 12
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | NL | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation Step 2 | bar: 2022-02-28 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Design Review II Presentation Step 3 | bar: 2022-03-14 to 2022-03-21
Software Testing Plan | bar: 2022-03-21
Design Review III Presentation
Peer Evaluation #3
Project Mini-Video Final
Completed Team Website
Capstone Poster
Capstone Presentation + Dry-run
Peer Evaluation #4
Final Product Acceptance Demo
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 criteria for countries (origin and current location)
9.5 improve initial log-in flow for github auth + email verification
9.6 Disable auth if api info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 study app
9.7.2 payments app
9.7.3 research app
9.7.4 participate app
9.7.5 profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: currently all email recipients are in the “to” field. Maybe we should send individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: currently this blocks on two different api calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 13
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | NL | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation Step 2 | bar: 2022-02-28 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Design Review II Presentation Step 3 | bar: 2022-03-14 to 2022-03-21
Software Testing Plan | bar: 2022-03-21 to 2022-03-28
Design Review III Presentation | bar: 2022-03-28
Peer Evaluation #3
Project Mini-Video Final
Completed Team Website
Capstone Poster
Capstone Presentation + Dry-run
Peer Evaluation #4
Final Product Acceptance Demo
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 criteria for countries (origin and current location)
9.5 improve initial log-in flow for github auth + email verification
9.6 Disable auth if api info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 study app
9.7.2 payments app
9.7.3 research app
9.7.4 participate app
9.7.5 profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: currently all email recipients are in the “to” field. Maybe we should send individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: currently this blocks on two different api calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 14
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | NL | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation Step 2 | bar: 2022-02-28 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Design Review II Presentation Step 3 | bar: 2022-03-14 to 2022-03-21
Software Testing Plan | bar: 2022-03-21 to 2022-03-28
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final
Completed Team Website
Capstone Poster
Capstone Presentation + Dry-run
Peer Evaluation #4
Final Product Acceptance Demo
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 criteria for countries (origin and current location)
9.5 improve initial log-in flow for github auth + email verification
9.6 Disable auth if api info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 study app
9.7.2 payments app
9.7.3 research app
9.7.4 participate app
9.7.5 profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: currently all email recipients are in the “to” field. Maybe we should send individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: currently this blocks on two different api calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 15
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | NL | 2022-04-18 | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation Step 2 | bar: 2022-02-28 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Design Review II Presentation Step 3 | bar: 2022-03-14 to 2022-03-21
Software Testing Plan | bar: 2022-03-21 to 2022-03-28
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final | bar: 2022-04-11
Completed Team Website | bar: 2022-04-11
Capstone Poster | bar: 2022-04-11
Capstone Presentation + Dry-run | bar: 2022-04-11
Peer Evaluation #4
Final Product Acceptance Demo
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 Custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 Criteria for countries (origin and current location)
9.5 Improve initial log-in flow for github auth + email verification
9.6 Disable social account auth if API info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 Study app
9.7.2 Payments app
9.7.3 Research app
9.7.4 Participate app
9.7.5 Profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: Currently all email recipients are in the “to” field. Consider sending individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: Currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: Currently this blocks on two different API calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 16 (Reading Week)
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | NL | 2022-04-25 | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation Step 2 | bar: 2022-02-28 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Design Review II Presentation Step 3 | bar: 2022-03-14 to 2022-03-21
Software Testing Plan | bar: 2022-03-21 to 2022-03-28
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final | bar: 2022-04-11 to 2022-04-18
Completed Team Website | bar: 2022-04-11 to 2022-04-18
Capstone Poster | bar: 2022-04-11 to 2022-04-18
Capstone Presentation + Dry-run | bar: 2022-04-11 to 2022-04-18
Peer Evaluation #4 | bar: 2022-04-18
Final Product Acceptance Demo | bar: 2022-04-18
Project Completion Work
Final (as-built) Report
Team Reflection Document
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 Custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 Criteria for countries (origin and current location)
9.5 Improve initial log-in flow for github auth + email verification
9.6 Disable social account auth if API info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 Study app
9.7.2 Payments app
9.7.3 Research app
9.7.4 Participate app
9.7.5 Profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: Currently all email recipients are in the “to” field. Consider sending individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: Currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: Currently this blocks on two different API calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded

## Week 17 (Finals Week)
| Week of: | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | NL | 2022-05-02
Sprint/Class Tasks: | Sprint User Stories:
1. Home Page | 1.1 I can access a styled homepage for GeekSurvey | bar: 2021-12-13 to 2021-12-20
1.2 I can navigate the web application from the home page | bar: 2021-12-13 to 2021-12-20
2. User Account Creation | 2.1 I can sign up, sign in, and sign out | bar: 2022-01-03 to 2022-01-17
2.2 I can edit my profile | bar: 2022-01-03 to 2022-01-17
2.3 I can view my profile | bar: 2022-01-03 to 2022-01-17
2.4 My profile contains all necessary information | bar: 2022-01-03 to 2022-01-17
2.4.1 Age | bar: 2022-01-03 to 2022-01-17
2.4.2 Level of Education | bar: 2022-01-03 to 2022-01-17
2.4.3 Balance (USD) | bar: 2022-01-03 to 2022-01-17
2.4.3.1 Balance should not be editable by the user | bar: 2022-01-03 to 2022-01-17
2.4.4 Years of Professional Experience | bar: 2022-01-03 to 2022-01-17
2.4.5 Occupation | bar: 2022-01-03 to 2022-01-17
Communication Memo | bar: 2022-01-17
Software Design Document Draft | bar: 2022-01-17 to 2022-01-31
3. Study Creation | 3.1 When logged in, I can create a study | bar: 2022-01-24 to 2022-01-31
3.2 I can view a study I previously created | bar: 2022-01-24 to 2022-01-31
3.2.1 A public landing page for every study on the site. accessible by unique URL | bar: 2022-01-24 to 2022-01-31
3.3 I can edit a study I previously created | bar: 2022-01-24 to 2022-01-31
3.4 The study contains a title and description | bar: 2022-01-24 to 2022-01-31
3.5 The study contains a creation date and expiry date | bar: 2022-01-24 to 2022-01-31
3.6 The study contains a list of enrolled accounts | bar: 2022-01-24 to 2022-01-31
3.7 The study contains enrollment criteria | bar: 2022-01-24 to 2022-01-31
3.8 Valid participants can enroll in the study | bar: 2022-01-24 to 2022-01-31
3.9 Invalid participants cannot enroll in the study | bar: 2022-01-24 to 2022-01-31
3.10 The study contains a balance (USD) | bar: 2022-01-24 to 2022-01-31
3.11 The study contains a payout amount (USD) | bar: 2022-01-24 to 2022-01-31
3.12 The study contains a completion code and external survey link | bar: 2022-01-24 to 2022-01-31
Software Design Document Final | bar: 2022-01-31 to 2022-02-07
Peer Evaluation #1 | bar: 2022-02-07
4. Study Discovery | 4.1 I can see a web page with a list of Studies | bar: 2022-02-07 to 2022-02-14
4.1.1 The web page only shows me Studies for which I am eligible for enrollment | bar: 2022-02-07 to 2022-02-14
4.1.2 The web page only shows me Studies which have not expired | bar: 2022-02-07 to 2022-02-14
4.2 I can click on a Study to go to its landing page | bar: 2022-02-07 to 2022-02-14
4.3 I can receive email notifications when a Study is created | bar: 2022-02-07 to 2022-02-14
4.3.1 I only receive study notifications if I'm eligible for the study | bar: 2022-02-07 to 2022-02-14
5. Study Completion | 5.1 The study contains a list of accounts who have completed it | bar: 2022-01-24 to 2022-01-31
5.2 The study adds users to this list when they enter the completion code | bar: 2022-01-24 to 2022-01-31
UGRADS Registration | bar: 2022-02-14 to 2022-02-21
6. Admin Menu | 6.1 I can view Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.2 I can edit Accounts and Profiles from the admin menu | bar: 2022-02-07 to 2022-02-14
6.3 I can view Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.4 I can edit Studies from the admin menu | bar: 2022-02-07 to 2022-02-14
6.5 I can log into the admin menu with a secure password | bar: 2022-02-07 to 2022-02-14
6.6 I can create a working admin account upon deployment
6.6.1 Documentation
Design Review II Presentation Step 1 | bar: 2022-02-21 to 2022-02-28
7. External Payments | 7.1 GeekSurvey's can send and receive funds through an external payment system | bar: 2022-02-21 to 2022-03-07
7.2 I can fund my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.3 I can fund my study from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.4 My study can automatically update balances for completing participants | bar: 2022-02-21 to 2022-03-07
7.5 I can cash out my balance from my study to my geeksurvey account | bar: 2022-02-21 to 2022-03-07
7.6 I can cash out my balance from my geeksurvey account | bar: 2022-02-21 to 2022-03-07
8. CRUNCH | 8.1 I can delete studies | bar: 2022-02-28 to 2022-03-07
8.2 I can customize my study’s expiration date | bar: 2022-02-28 to 2022-03-07
8.3 I can set a maximum number of participants in a study | bar: 2022-02-28 to 2022-03-07
8.3.1 Participants cannot enroll when the maximum is reached | bar: 2022-02-28 to 2022-03-07
8.4 I can remove participants who are enrolled in my study | bar: 2022-02-28 to 2022-03-07
8.5 I can approve or deny compensation for participants who completed my study | bar: 2022-02-28 to 2022-03-07
8.6 I can opt in or out of email notifications (opt out by default) | bar: 2022-02-28 to 2022-03-07
Design Review II Presentation Step 2 | bar: 2022-02-28 to 2022-03-07
Alpha Prototype Demo | bar: 2022-02-28 to 2022-03-07
Peer Evaluation #2 | bar: 2022-03-07
Design Review II Presentation Step 3 | bar: 2022-03-14 to 2022-03-21
Software Testing Plan | bar: 2022-03-21 to 2022-03-28
Design Review III Presentation | bar: 2022-03-28 to 2022-04-04
Peer Evaluation #3 | bar: 2022-04-04
Project Mini-Video Final | bar: 2022-04-11 to 2022-04-25
Completed Team Website | bar: 2022-04-11 to 2022-04-18
Capstone Poster | bar: 2022-04-11 to 2022-04-18
Capstone Presentation + Dry-run | bar: 2022-04-11 to 2022-04-18
Peer Evaluation #4 | bar: 2022-04-18
Final Product Acceptance Demo | bar: 2022-04-18 to 2022-04-25
Project Completion Work | bar: 2022-04-25
Final (as-built) Report | bar: 2022-04-25
Team Reflection Document | bar: 2022-04-25
Final Project Delivery
Peer Evaluation #5
9. Overflow (STRETCH GOALS) | 9.1 Change profile age to a birthdate as a proper date field.
9.2 Customizable expiration date to studies (MOVED TO SPRINT 8: CRUNCH)
9.3 Bootstrap for better UX
9.3.1 Custom elements and color schemes
9.4 More enrollment criteria per client request
9.4.1 Criteria for countries (origin and current location)
9.5 Improve initial log-in flow for github auth + email verification
9.6 Disable social account auth if API info not defined in .env
9.7 Reorganize code into apps? Researcher code in researchers/ etc.
9.7.1 Study app
9.7.2 Payments app
9.7.3 Research app
9.7.4 Participate app
9.7.5 Profile app
9.8 Check if user is authenticated through GitHub
9.9 Display GitHub avatar if user is authenticated through GitHub
9.10 Add GitHub enrollment criteria
9.10.1 Add GitHub account age
9.11 Move study_email_helper to a custom signal that fires upon study creation
9.12 I can’t see other email recipients in the group email for study notifications NOTE: Currently all email recipients are in the “to” field. Consider sending individual emails instead of a batch email
9.13 Email notifications are parallelized NOTE: Currently this blocks an http response upon study creation
9.14 Claims are parallelized NOTE: Currently this blocks on two different API calls to PayPal
9.15 Fix the warning about naive datetime upon study creation
Legend
Done
TODO
Due
Winter Break
Spring Break
Now Line (NL)
Class Deliverables | Red Text and Italicized and Bolded