## HPVC Gantt Chart
Team: 2020 HPVC Capstone | [249 empty] | Color Key: |  | Everyone |  |  |  | Sam
Client: Perry Wood
Team Members: Anuththara Allujjage, Allison Bedrin, Ryan Podell, Samantha Robbins, Sebastian Ruvalcaba and Paolo Quattrociocchi
Gantt Chart: Summer Semester
6/1/2020 - 8/14/2020 |  |  | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [6 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Week 1 | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Week 1 | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [11 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [11 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | June | [6 empty] | June | [6 empty] | June | [6 empty] | June | [6 empty] | June | [6 empty] | July | [6 empty] | July | [6 empty] | July | [6 empty] | July | [6 empty] | August
|  |  | M | T | W | TH | F | SA | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | Sun | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | Sun | M | T | W | TH | F | Sa | Su | M | T | W | TH | F | Sa | Sa | M | T | W | TH | F | Sa | Sa | M | T | W | TH | F | Sa | Sa | M | T | W | TH | F | Sa | Sa | M | T | W | TH | F | Sa | Sa | M | T | W | TH | F | Sa | Sa | M | T | W | TH | F | Sa | Sa | M | T | W | TH | F | Sa | Su
Description | Activity Due Date | Responsibility | time axis 2019-07-29 to 2020-08-09
Meetings: | bar: 2019-12-25; 2020-01-01
Team Meetings (Zoom call without Dr. Trevas) | Recurring | bar: 2019-11-20; 2019-11-27 to 2019-11-29; 2019-12-04; 2019-12-25; 2020-01-01; 2020-06-04; 2020-06-09; 2020-06-16; 2020-06-23; 2020-06-30; 2020-07-07; 2020-07-14; 2020-07-21; 2020-07-28; 2020-08-04
Staff Meetings (Have individual action items completed) | Recurring |  | 2019-11-01: Pour
Assignments: | bar: 2019-12-25; 2020-01-01
Team Charter | 2020-06-14 |  | 2020-04-06: Rain Out; 2020-04-07: Rain Out; 2020-04-08: Rain Out; 2020-04-09: Rain Out; 2020-04-10: Rain Out
[80 empty] | Hydro Test | [10 empty] | A | A | [21 empty] | A | [5 empty] | A
[91 empty] | Y | Y | [21 empty] | Y | [5 empty] | Y
[102 empty] | night tie-in | [11 empty] | D | [5 empty] | D
[114 empty] | A | [5 empty] | A
[114 empty] | D | [5 empty] | D
DISINFECTION
[202 empty] | Rain Out | Rain Out | Rain Out | Rain Out | Rain Out |  | Rain Out | [36 empty] | TIE-IN
[114 empty] | A | [5 empty] | A
[114 empty] | Y | [5 empty] | Y
[44 empty] | Pour | [10 empty] | Pour |  |  |  | Pour
WML
WML
[6 empty] | Rebar | [6 empty] | Pour | [22 empty] | Pour | [22 empty] | Pour |  |  | Pour
[6 empty] | Pour Wall 12 | [9 empty] | Pour Wall | [6 empty] | Pour Wall |  | Pour Wall | [21 empty] | Pour | [18 empty] | Pour | [7 empty] | Pour
[47 empty] | Pour |  | Pour |  |  |  | Pour
Pour
CLSM
[74 empty] | Pour |  |  | Pour |  |  | Pour
[202 empty] | Rain Out | Rain Out | Rain Out | Rain Out | Rain Out
RAT

## Sheet1
HPVC Capstone Team 2020
Allison Bedrin, Samantha Robbins, Ryan, Sebastian, Anuththara, Paolo
3 Week Look Ahead Schedule
Week of 06-05-2020 |  |  | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [6 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Week 1 | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Week 1 | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [11 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [11 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Previous Week | [5 empty] | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3
|  |  | M | T | W | TH | F | SA | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | Sun | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa | M | T | W | TH | F | Sa
Description | Activity ID | Responsibility | time axis 2019-07-29 to 2020-06-27
Yard/Site Piping/Demo |  | WML | bar: 2019-11-20; 2019-11-27 to 2019-11-29; 2019-12-04; 2019-12-25; 2020-01-01
Install Ductbank DB 201.1/201.2/205.1/300 | 4555 | Southern | 2019-11-01: Pour
6" MBR Drain to MH | 12110 | Southern | bar: 2019-08-23; 2019-08-26 to 2019-08-27
Install Fiber Optic | 4480 / 4595 / 4675 | Southern | 2020-04-06: Rain Out; 2020-04-07: Rain Out; 2020-04-08: Rain Out; 2020-04-09: Rain Out; 2020-04-10: Rain Out
24" Aeration Basin Feed | 4400 | WML-Ernesto | 2019-11-01: Hydro Test; 2019-11-28: A; 2019-11-29: A; 2019-12-25: A; 2020-01-01: A
Install 48" Aeration Basin Effluent #3 and #4 | 4405 | WML-Ernesto | bar: 2019-09-04 to 2019-09-06; 2019-09-09; 2019-09-23 to 2019-09-25; 2019-10-08; 2019-11-26; 2019-11-28 to 2019-11-29; 2019-12-25; 2020-01-01; 2020-03-09
24" Storm Drain | 4160 | WML-Ernesto | bar: 2019-08-19 to 2019-08-23; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-27; 2019-10-07 to 2019-10-11; 2019-10-14; 2019-10-17 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-10-29; 2019-10-31 to 2019-11-01; 2020-03-09
Plant Effluent Tie-in and Backfill | 4250 | WML-Ernesto | 2019-12-11: night tie-in; 2019-12-25: D; 2020-01-01: D
16" RW Distribution Line | 4165 | WML-Ernesto | bar: 2019-09-04 to 2019-09-06; 2019-09-09; 2019-09-23 to 2019-09-25; 2019-10-08; 2019-12-17 to 2019-12-19; 2019-12-25; 2020-01-01; 2020-03-09
Install Standby Generator | 4677 | WML-Ernesto | bar: 2019-09-04 to 2019-09-06; 2019-09-09; 2019-09-23 to 2019-09-25; 2019-10-08; 2019-12-17 to 2019-12-19; 2019-12-25; 2019-12-30 to 2020-01-01; 2020-03-09
Install Potable Water Line | 4195 | WML-Ernesto | 2020-05-28: DISINFECTION; 2020-06-02: MOPO
Install NPW | 4225 | WML-Ernesto | 2020-04-06: Rain Out; 2020-04-07: Rain Out; 2020-04-08: Rain Out; 2020-04-09: Rain Out; 2020-04-10: Rain Out; 2020-04-13: Rain Out; 2020-05-26: TIE-IN; 2020-06-03: TIE-IN
30" MBR Effluent Tie-In at UV | 4245 | WML-Ernesto | 2020-06-04: Hydro Test; 2020-06-11: TIE-IN
Install UG GAS Line | 4190 | WML-Ernesto | bar: 2019-09-04 to 2019-09-06; 2019-09-09; 2019-09-23 to 2019-09-25; 2019-10-08; 2019-12-17 to 2019-12-19; 2019-12-30 to 2019-12-31; 2020-04-06 to 2020-04-10; 2020-04-24; 2020-04-27; 2020-06-08 to 2020-06-12; 2020-06-15 to 2020-06-19
Headworks Screen |  | WML | bar: 2019-12-25; 2020-01-01
Foul Air, Drain & NPW Piping | 6095 / 6100 / 6105 | WML-Denis | bar: 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-27; 2019-12-30 to 2020-01-03; 2020-01-06 to 2020-01-09; 2020-01-21 to 2020-01-22
Install Ductbank 50.1 /104 | 4510/4540 | WML/Southern | 2019-09-20: Pour; 2019-10-03: Pour; 2019-10-08: Pour
Install Ductbank 50.1 /105 | 6055 | WML/Southern | bar: 2019-08-26 to 2019-08-28
Install Ductbank 50.1 /106 | 6085 | WML/Southern | bar: 2019-08-26 to 2019-08-28; 2019-09-30 to 2019-10-01
Install Ductbank 50.1 /107 | 6090 | WML/Southern | bar: 2019-08-26 to 2019-08-28; 2019-10-02
F/R/P Pipe Supports | 7130 | WML-Jaime | bar: 2019-08-26 to 2019-08-28; 2019-10-02; 2019-12-12 to 2019-12-13; 2019-12-19 to 2019-12-20; 2019-12-23
Install Media - Odor Control | 6210 | WML-Armando | bar: 2019-09-27; 2019-09-30; 2020-05-11
Load Media/Carbon | 6210 | WML-Armando | bar: 2019-09-27; 2019-09-30; 2020-05-21 to 2020-05-22; 2020-06-04
Test FRP | 6095 | WML-Martin | bar: 2019-09-27; 2019-09-30; 2020-05-26 to 2020-05-27
Install Analyzer Panel | N/A | Southern | bar: 2019-09-27; 2019-09-30; 2020-05-26 to 2020-05-28; 2020-06-04 to 2020-06-05
Grit Chamber
Influent Pump Station |  | WML | bar: 2020-03-06; 2020-03-09
16" Pipe encasement | 8090 | WML-Ernesto | bar: 2020-03-06; 2020-03-09; 2020-05-07; 2020-06-10 to 2020-06-11
Install 12" Foul Air | 8095 | WML-Martin | bar: 2020-03-06; 2020-03-09; 2020-05-26 to 2020-05-27
Install Influent Pumps & Piping | 8100/8105 | WML-Martin | bar: 2020-03-06; 2020-03-09; 2020-04-29 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-15; 2020-05-18 to 2020-05-22; 2020-05-26
Install Electrical Conduits/Control Panels/Cabling | 8002/8130/8145 | Southern | bar: 2020-03-06; 2020-03-09; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-15; 2020-05-18 to 2020-05-22; 2020-05-26 to 2020-05-29; 2020-06-01 to 2020-06-04
Remove IPS Bypass Plugs | 8155 | WML-Ernesto | bar: 2020-03-06; 2020-03-09; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-15; 2020-05-18 to 2020-05-22; 2020-06-11
Install Secondary Bypass | 8120 | WML-Ernesto | bar: 2020-03-06; 2020-03-09; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-15; 2020-05-18 to 2020-05-22; 2020-06-04 to 2020-06-05
Install Planking and Beams | 8125 | WML-Armando | bar: 2020-03-06; 2020-03-09; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-20 to 2020-05-21
Pour Grout Pads | 8100 | WML-Armando | bar: 2020-03-06; 2020-03-09; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-20
T-Lock Repair | 8110 | Parada | bar: 2020-03-06; 2020-03-09; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-22
Fine Screens |  | WML
Install FRP Planking | 9095 | WML-Armando | bar: 2019-08-28 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-07; 2020-02-06 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-05-11
Manufacturers Start Up and Test Screw Conveyor | 21115 | WML-Armando | bar: 2019-08-28 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-12 to 2020-02-14; 2020-02-26 to 2020-02-28; 2020-03-13; 2020-03-24 to 2020-03-27; 2020-04-21 to 2020-04-23
Dry Pack Pipe Supports | N/A | WML-Armando | bar: 2019-08-28 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-12 to 2020-02-14; 2020-02-26 to 2020-02-28; 2020-03-13; 2020-03-24 to 2020-03-27; 2020-04-21 to 2020-04-23; 2020-05-21 to 2020-05-22
Install Analyzer Panel | N/A | Southern | bar: 2019-09-27; 2019-09-30; 2020-05-26 to 2020-05-28; 2020-06-04 to 2020-06-05
MBR Building |  | WML
Metal Building Assembly / Punchlist | 12200 | G&W | bar: 2019-08-19 to 2019-08-23; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-23 to 2019-09-27; 2019-09-30 to 2019-10-04; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-18 to 2019-11-19; 2019-11-21 to 2019-11-22; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-17; 2020-01-20 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09; 2020-04-27 to 2020-04-29
Wall Fix and Punchlist | 12200 | G&W | bar: 2019-08-19 to 2019-08-23; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-23 to 2019-09-27; 2019-09-30 to 2019-10-04; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-18 to 2019-11-19; 2019-11-21 to 2019-11-22; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-17; 2020-01-20 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09; 2020-04-27 to 2020-04-29; 2020-06-08 to 2020-06-12
Install Lighting & Devices | 12555 | Southern | bar: 2019-09-13; 2019-09-16 to 2019-09-18; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-19; 2019-11-21 to 2019-11-22; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-17; 2020-01-20 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-23 to 2020-03-27; 2020-03-30 to 2020-04-03; 2020-04-06 to 2020-04-10; 2020-04-13 to 2020-04-17; 2020-04-20 to 2020-04-24; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-15; 2020-05-18 to 2020-05-22; 2020-05-26 to 2020-05-29; 2020-06-01 to 2020-06-02
Install Countertop at Laboratory | 12420 | Cabinetry | bar: 2019-09-13; 2019-09-16 to 2019-09-18; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-10-29; 2019-10-31 to 2019-11-01; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-17; 2020-01-20 to 2020-01-24; 2020-03-03 to 2020-03-06; 2020-03-27; 2020-05-12; 2020-06-04 to 2020-06-05
Small Diameter Pipe and Instrumentation | 12385 | WML-Martin | bar: 2019-11-25; 2020-01-22 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-03-23 to 2020-03-27; 2020-03-30 to 2020-04-03; 2020-04-06 to 2020-04-10; 2020-04-13 to 2020-04-17; 2020-04-20 to 2020-04-24; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-15; 2020-05-18 to 2020-05-22; 2020-05-26 to 2020-05-29; 2020-06-01 to 2020-06-05; 2020-06-08 to 2020-06-12
Install MBR Feed Pumps and Piping | 12240/12330 | Parada | bar: 2019-11-18
Coat Above Ground Piping | 12480 | Parada | bar: 2019-11-18; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-25 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-03-23 to 2020-03-27; 2020-03-30; 2020-04-06; 2020-04-17; 2020-04-20; 2020-05-05 to 2020-05-08
Install Doors and Hardware | 12235 / 12315 | WML-Armando | bar: 2019-11-18; 2020-02-25 to 2020-02-28; 2020-03-02 to 2020-03-04
MBR Permeate Piping | 12335 | WML-Martin | bar: 2019-10-29; 2019-10-31; 2019-11-18 to 2019-11-19; 2019-11-21 to 2019-11-22; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-02-05 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-25; 2020-03-06; 2020-03-09; 2020-03-25 to 2020-03-27; 2020-03-30 to 2020-04-02
RO Piping/Support Install | 12345/12350/12355 | WML-Martin | bar: 2019-08-29 to 2019-08-30; 2019-09-20; 2019-09-23 to 2019-09-27; 2019-09-30 to 2019-10-04; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28; 2019-11-01; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-05 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-25; 2020-03-06; 2020-03-09; 2020-03-25 to 2020-03-27; 2020-03-30 to 2020-04-02
RO Equipment Anchor | 12195 | WML-Martin | bar: 2019-08-29 to 2019-08-30; 2019-09-11 to 2019-09-13; 2019-09-19; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-05 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-25; 2020-03-06; 2020-03-09; 2020-03-25 to 2020-03-27; 2020-03-30 to 2020-04-02
Install Louvers | 12310 | AMS | bar: 2019-08-29 to 2019-08-30; 2019-09-11 to 2019-09-13; 2019-09-19; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-03-04 to 2020-03-06; 2020-04-13 to 2020-04-17
Install HVAC | 12415 | AMS | bar: 2019-08-29 to 2019-08-30; 2019-09-11 to 2019-09-13; 2019-09-19; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-26 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-03-23 to 2020-03-27; 2020-03-30 to 2020-04-03; 2020-04-06 to 2020-04-10; 2020-04-13 to 2020-04-17; 2020-04-20 to 2020-04-24; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-15
Install Exhaust Fans | 12305 | AMS | bar: 2019-08-29 to 2019-08-30; 2019-09-11 to 2019-09-13; 2019-09-19; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-26 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-05-29; 2020-06-09 to 2020-06-12
Install FRP Planking | 12225 | WML-Armando | bar: 2019-08-29 to 2019-08-30; 2019-09-11 to 2019-09-13; 2019-09-19; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-26 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-04-29 to 2020-05-01; 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-12
Install FRP Weirs | N/A | WML-Armando | bar: 2019-08-29 to 2019-08-30; 2019-09-11 to 2019-09-13; 2019-09-19; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-26 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-05-13 to 2020-05-14
Bridge Crane Installation Load Test | 12215 | OCIENG | 2020-06-04: Load Test
Unload and Store MBR Cassettes | 12255 | WML-Martin | bar: 2019-08-29 to 2019-08-30; 2019-09-11 to 2019-09-13; 2019-09-19; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-26 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-06-12
Asasemble MBR Cassette Frames and Install | 12260 | WML-Martin | bar: 2019-08-29 to 2019-08-30; 2019-09-11 to 2019-09-13; 2019-09-19; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-02-26 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-06-15 to 2020-06-19
Aeration Basin |  | WML
Install RAS Piping Tank 1 & 2 / Hydrotest | 11220 | WML-Martin | bar: 2019-09-16 to 2019-09-20; 2019-09-23
Coat RAS Pipe Tank 1 & 2 | 11315 | Parada | bar: 2019-09-04 to 2019-09-06
F/R/S Aeration Basin SOG | 11040 | WML-Jaime | 2019-08-01: Rebar; 2019-08-16: Pour; 2019-09-12: Pour; 2019-10-08: Pour; 2019-10-11: Pour
F/R/S Aeration Basin Walls | 11055/75/80/85 | WML-Jaime | 2019-08-01: Pour Wall 12; 2019-08-20: Pour Wall; 2019-08-28: Pour Wall; 2019-08-30: Pour Wall; 2019-09-24: Pour; 2019-10-16: Pour; 2019-10-25: Pour
Grade SOG | 11020 | WML-Jaime | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18
Backfill AB Structure | 4084 | JK | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-11-18 to 2019-11-19
Install Mix Liquor Recycle Pipe Supports | 11230 | WML-Jaime | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-11-18 to 2019-11-19; 2019-11-21 to 2019-11-22; 2019-11-25
Install Gates | 11180/11185/11190 | WML-Jaime | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-11-01; 2019-11-18 to 2019-11-19; 2019-11-21 to 2019-11-22; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-10; 2019-12-26 to 2019-12-27
Install Air Piping Supports | 11225 | WML-Jaime | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-10-29; 2019-11-18 to 2019-11-19; 2019-11-21 to 2019-11-22; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-10
Install Handrails | 11215 | WML-Denis | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-11-18 to 2019-11-19; 2019-11-21 to 2019-11-22; 2019-11-25 to 2019-11-26; 2020-02-10 to 2020-02-14
Install Eductor Mixers | 11245 | WML-Denis | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-11-25; 2020-02-10 to 2020-02-14
Walkway Rebar/Pour | 11145/11150 | WML-Denis | 2019-09-24: Pour; 2019-09-26: Pour; 2019-10-01: Pour
Walkway concealed electrical conduit | 11023 | WML-Denis | bar: 2019-07-29 to 2019-08-02; 2019-08-12 to 2019-08-16; 2019-08-19; 2019-09-23 to 2019-09-25; 2020-02-10 to 2020-02-14
False Work | 11140 | WML-Denis | bar: 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-09-27; 2019-10-07 to 2019-10-11; 2020-02-10 to 2020-02-14
Aeration Basin - Hydrotest Influent Box #1 | 11200 | WML-Denis | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-12; 2020-02-10 to 2020-02-14
Aeration Basin - Hydrotest Tanks 1 and 2 | 11200 | WML-Denis | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-12-12 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2020-02-10 to 2020-02-14
Install Control Panels and Pull Wire | 11280/11290/11295 | Southern | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-14; 2020-02-06 to 2020-02-07; 2020-02-10 to 2020-02-14
Install Fine Bubble Diffusers | 11255 | WML-Armando | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-14; 2020-02-14; 2020-02-17 to 2020-02-21
F/P/S North/South Stairway Pads | 12205 | WML-Armando | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-14; 2020-02-14; 2020-02-17 to 2020-02-21; 2020-03-06; 2020-05-21 to 2020-05-22
Install North/South Stairway | 12205 | WML-Armando | bar: 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-18; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-14; 2020-05-26 to 2020-05-29; 2020-06-01
Install Pipe Supports for Air Pipe | 12360 | WML-Armando | 2020-05-11: Pour
Install Diffusers | 11260 | WML-Armando | bar: 2019-10-21 to 2019-10-24; 2020-03-30 to 2020-04-04; 2020-04-14; 2020-06-01 to 2020-06-02; 2020-06-10 to 2020-06-12; 2020-06-15
Chemical Tank Farm |  | WML
Overex, Encase existing Pipe, Grade SOG | 15005 | WML-Robert | 2019-10-11: CLSM
F/R/P/S Slab | 15015 | WML-Jaime | 2019-10-25: Pour; 2019-10-29: Pour; 2019-11-01: Pour
Install AG Chemical Lines | UFB03.38 | WML-Martin | 2020-04-06: Rain Out; 2020-04-07: Rain Out; 2020-04-08: Rain Out; 2020-04-09: Rain Out; 2020-04-10: Rain Out
Install UG Chemical Lines / Set Vaults | UFB03.34 | WML-Martin | bar: 2019-10-21 to 2019-10-24; 2020-03-30 to 2020-04-04; 2020-04-14
Install FRP Ladders | N/A | WML-Martin | bar: 2019-10-21 to 2019-10-24; 2020-03-30 to 2020-04-04; 2020-04-14; 2020-05-15
Install AG Conduit & Control Panel | 15070/15075/15080 | WML/Southern | 2020-04-06: Rain Out; 2020-04-07: Rain Out; 2020-04-08: Rain Out; 2020-04-09: Rain Out; 2020-04-10: Rain Out
Chemical Storage #2 |  | WML
Set Control Panels and Pull Wire | 15075 | WML/Southern | bar: 2020-02-07; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-20; 2020-03-23 to 2020-03-27; 2020-04-02 to 2020-04-03; 2020-04-14 to 2020-04-15; 2020-04-27
Install FRP Ladders | N/A | WML-Armando | bar: 2020-02-07; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-20; 2020-03-23 to 2020-03-27; 2020-04-02 to 2020-04-03; 2020-04-14 to 2020-04-15; 2020-05-08; 2020-05-15; 2020-05-18 to 2020-05-19
Install UG Chemical Lines | 15065 | WML-Ernesto | bar: 2020-05-11 to 2020-05-15; 2020-06-04 to 2020-06-05
Install AG Chemical Lines | 15065 | WML-Martin | bar: 2020-04-23 to 2020-04-24; 2020-04-27 to 2020-04-29
Install Pump Skid and Piping | 15065 | WML-Martin | bar: 2020-04-23 to 2020-04-24; 2020-04-27 to 2020-04-29; 2020-06-15 to 2020-06-19
Move lighting panel | N/A | WML/Southern | bar: 2020-04-23 to 2020-04-24; 2020-04-27 to 2020-04-29; 2020-06-03 to 2020-06-04
Recycled Water Pump Station |  | WML
Backfill | 14025 | WML - Martin | bar: 2019-08-22 to 2019-08-23
F/R/P/ Slab | 14040 | WML-Jaime | bar: 2019-09-23 to 2019-09-27; 2019-11-18
Duct Bank |  | Southern
Dig/Lay/Backfill 24" Effluent Lines | 4235 | WML-Ernie | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16
12"/18" RW Install Pumps & Piping | 14055 / 14070 | WML-Denis | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2019-11-18 to 2019-11-19
6" NPW Install Pumps & Piping | 14075 / 14080 | WML-Denis | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2019-11-21 to 2019-11-22; 2019-11-25
Grout Pumps | 14055 | WML-Denis | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2019-11-21 to 2019-11-22; 2019-11-25; 2019-12-18 to 2019-12-19
Paint AG Pipe | 14115 | Parada | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2020-01-06; 2020-02-03 to 2020-02-05
Install Misc. Metals | 14050 | WML-Armando | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2020-01-06; 2020-02-05 to 2020-02-06
Install FRP Planking | 14050 | WML-Armando | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2020-01-06; 2020-02-05 to 2020-02-06; 2020-05-11 to 2020-05-12
Install Pump Lifting Cables | 8145 | WML-Armando | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2020-01-06; 2020-02-05 to 2020-02-06; 2020-05-22; 2020-05-28
Install Sample Panel and Piping | N/A | WML-Martin | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2020-01-06; 2020-02-05 to 2020-02-06; 2020-05-22; 2020-06-15 to 2020-06-17
Install NPW Piping | 14080 | WML-Martin | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2020-01-06; 2020-02-05 to 2020-02-06; 2020-05-15; 2020-05-18
Storm Water Pump Station |  | WML | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16
Install and Lift Pumps | 4115 | WML-Denis | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2019-12-09 to 2019-12-10
Install LCP and Instrumentation | 4125 | WML/Southern | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2019-12-23; 2019-12-26; 2020-01-08 to 2020-01-10; 2020-01-13 to 2020-01-15; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14
UG Conduit & Cables | 4140 | WML/Southern | bar: 2019-07-31 to 2019-08-01; 2019-08-12 to 2019-08-16; 2019-12-23; 2019-12-26; 2020-01-08 to 2020-01-10; 2020-01-13 to 2020-01-15; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-05-15
Electrical Building |  | WML
Metal Building | 20040 | G&W | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-25
Install HVAC Equipment & Ductwork | 20050 | AMS | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-25; 2020-01-14 to 2020-01-15
Install XMFR-HW | 4560 | Southern | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-25; 2019-10-15 to 2019-10-18
Install Electrical Equipment | 20060 | Southern | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-09-23 to 2019-09-27; 2019-09-30 to 2019-10-04; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-18 to 2019-11-19; 2019-11-21 to 2019-11-22; 2019-12-16 to 2019-12-17
Install Lighting and Devices | 20085 | Southern | bar: 2019-09-13; 2019-09-16 to 2019-09-18; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-22; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-18
Install Doors | 20045 | Southern | bar: 2019-09-13; 2019-09-16 to 2019-09-18; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-10-29; 2019-10-31 to 2019-11-01; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13
Pull Wire/Terminate - HVAC | 20070 | Southern | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-25; 2019-10-15 to 2019-10-18; 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-20 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-03-23 to 2020-03-27; 2020-04-07 to 2020-04-10; 2020-04-13 to 2020-04-17; 2020-04-20 to 2020-04-21; 2020-06-05
Relocate Generator | 20100 | Southern | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-25; 2019-10-15 to 2019-10-18; 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-20 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-03-23 to 2020-03-27; 2020-04-07 to 2020-04-10; 2020-04-13 to 2020-04-17; 2020-04-20 to 2020-04-21; 2020-06-15 to 2020-06-17
Check-out, Start-Up & Commissioning |  | WML | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-25; 2019-10-15 to 2019-10-18; 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-20 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-03-23 to 2020-03-27; 2020-04-07 to 2020-04-10; 2020-04-13 to 2020-04-17; 2020-04-20 to 2020-04-21
SCE Energization | N/A | SCE | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-25; 2019-10-15 to 2019-10-18; 2019-10-29; 2019-10-31 to 2019-11-01; 2019-11-25 to 2019-11-26; 2019-12-02 to 2019-12-03; 2019-12-05 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31; 2020-01-02 to 2020-01-03; 2020-01-20 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07; 2020-02-10 to 2020-02-14; 2020-02-17 to 2020-02-21; 2020-02-24 to 2020-02-28; 2020-03-02 to 2020-03-06; 2020-03-09 to 2020-03-13; 2020-03-16 to 2020-03-20; 2020-03-23 to 2020-03-27; 2020-04-07 to 2020-04-10; 2020-04-13 to 2020-04-17; 2020-04-20 to 2020-04-21; 2020-05-29
MBR Feed Pumps ORT and FAT | 21335 | Flo Systems | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-06-08 to 2020-06-12
Aeration & MBR Blowers | 21170 | Neuros | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-06-08 to 2020-06-10
NPW Pumps | 21440 | Muniquip | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-06-09 to 2020-06-11
I&C Check-out, Loop Testing & Instrument Checks | 6235/8150/9175/11310/12610/12615/12620 | TSI | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-05-08; 2020-05-13 to 2020-05-15; 2020-05-20 to 2020-05-21; 2020-06-04 to 2020-06-05
EATON VFD/MCC Repairs | N/A | EATON | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-05-08; 2020-05-13 to 2020-05-15; 2020-06-02 to 2020-06-05
IPS Start-up | 21055 | Flow N Control | 2020-06-04: ORT; 2020-06-09: FAT; 2020-06-15: RAT
Aeration Basin Diffuser | 21165 | EDI | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-05-08; 2020-05-13 to 2020-05-15; 2020-06-17 to 2020-06-19
WAS Pump Station | 21380 | Flow N Control | 2020-06-09: FAT
Storm Water Pump Station | 21635 | Flow N Control | 2020-06-09: FAT
RO Equipment Check-Up | 21350 | H20 Innovation | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-05-08; 2020-05-13 to 2020-05-15; 2020-06-08 to 2020-06-12; 2020-06-15 to 2020-06-19
MBR Equipment Check-Up | 21330 | Fibracast | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-05-08; 2020-05-13 to 2020-05-15; 2020-06-15 to 2020-06-19
Fine Screens Screw Conveyor | 21135 | Spirac | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-05-08; 2020-05-13 to 2020-05-15; 2020-06-16 to 2020-06-18
Barscreen and Washer Compactor | 21005 | Hubber / JWC | bar: 2019-07-29 to 2019-07-30; 2019-08-12 to 2019-08-16; 2019-08-26 to 2019-08-30; 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-13; 2020-05-08; 2020-05-13 to 2020-05-15; 2020-06-17 to 2020-06-19
T * = Training