## Only Purchases
Bill of Materials
Part Name | Quantity | Part # | Description | Single Part Price | Total Price | Vendor | Lead Time | Status | Make/Buy | Image
Pipe Insulation | 2 | ORP05812 | L=6.2 ft x D=1/4 inch | 9.2 | 18.4 | Amazon | 1 month | Ordered | Buy
Pipe | 1 | EPPW2012 | L=25ft x D=1/4 inch Di = 1/8 inch | 19.17 | 19.17 | Granger | 1 Week | Ordered | Buy
Pump | 1 | 517100002 | Fountain Pump | 217 | 217 | Grainger | 3 Days | Order February | Buy
Barbed T | 1 | ‎JWBTST6 | D=1/8in, Pack of 5, 3 way | 9.66 | 9.66 | Amazon | 1 Week | Ordered | Buy
Polyester Waterproof Tape | 1 | B07HCP3HXM | APT 3.5 thic polyester tape | 15.88 | 15.88 | Amazon | -------------------- | Received | Buy |  | 13.58
Activator | 1 | B0006IUWCC | fastcap super glue adhesive | 21.19 | 21.19 | Amazon | -------------------- | Received | Buy |  | 10.42
Super Glue | 1 | B01FWZNPUY | 20g bob smith super glue | 12.99 | 12.99 | Amazon | -------------------- | Received | Buy |  | 4
Thic Aluminum Sheet | 2 |  | 12inx12inx5/8in | 123.73 | 247.46 | Machine Shop | -------------------- | Received | Buy
Thin Aluminum Sheet | 2 | 9246K425 | 12inx48inx.25in | 165.97 | 331.94 | McMaster Carr | -------------------- | Received | Buy
Bolts | 1 | B01NBJT5OR | 1/4-20inx.5in pack:100 | 21.74 | 21.74 | McMaster Carr | Same Week | Ordered | Buy
Nuts | 1 | B07VG2569H | 1/4-20in pack:100 | 9.77 | 9.77 | McMaster Carr | Same Week | Ordered | Buy
2x4 Wood | 8 | 312528776 | 2inx4inx8ft | 3.75 | 30 | Home Depot | Same Day | Recieved | Buy
5 Gallon Bucket | 2 | 05GLHD2 | 5 gal hope depot bucket | 4.98 | 9.96 | Home Depot | Same Day | Recieved | Buy
Black Paint | 1 | 779402 | 1-gal | 48.48 | 48.48 | Home Depot | Same Day | Recieved | Buy
White Reflective Paint | 1 |  | reflective 1-gal | 50 | 50 | Home Depot | Same Day | Recieved | Buy
Thermometer | 1 | HH804W | 2 channel RTD | 142.86 | 142.86 | Omega | 5 Weeks | Order February | Buy
Thermocouples | 6 | 5LSC-5SRTC | 32-900F range | 166.42 | 998.52 | Omega | 4 Weeks | Partial Recieved/ Partially order Feb | Buy
Flow rate sensors | 2 | BV1000-2000-3000 | .1-2.5 LPM | 83 | 166 | Omega | 5 Weeks | Order February | Buy
Valves | 1 | SV6000-Series | .25 in dia 2 Way pack of 2 | 11 | 11 | Amazon | 1 Week | Ordered | Buy
Radiation Sensor | 1 | R8008 | RT-100 | 512.1 | 512.1 | JLW Instruments | 1 Week | Order February | Buy
Copper Coil | 1 | B0991Y99V2 | 1/8 dia, 6.56 ft long | 10.91 | 10.91 | Amazon | 1 Week | Ordered | Buy
Folding Table | 1 |  | 60 in long | 110 | 110 | Home Depot | Same Day | Recieved | Buy
Storage Tote | 1 | 301356003 | 38 gal | 39.98 | 39.98 | Home Depot | Same Day | Recieved | Buy
Gasket | 1 | 38R341 | 1/16 in Thick | 61.7 | 61.7 | Grainger | 3 Days | Received | Buy
NPT | 8 | 20YZ84 | 1/8 in .75 in length | 4.66 | 37.28 | Grainger | 3 Days | Partially Odered/ Partially Recieved | Buy
Mylar Film | 1 | B07WP3NKN7 | 6 pack 210cmx130cm | 10.97 | 10.97 | Amazon | Same Week | Ordered | Buy
Teflon Tape | 1 | B07F3QTDH7 | .5 in 30ft long | 0.98 | 0.98 | Home Depot | Same Day | Received | Buy
Medium Aluminum Sheet | 1 | 8975K158 | 12"x36"x5/8" | 186.82 | 186.82 | McMaster Carr | Same Week | Ordered | Buy
|  |  |  | Total Price: | 3352.76
|  |  | Tax & Shipping | Total Price + 20% | 4023.312
|  |  | With 5% Contingency | Final Price | 4224.4776

## Purchases or Made
Bill of Materials
Part Name | Quantity | Part # | Description | Single Part Price | Total Price | Vendor | Lead Time | Status | Make/Buy | Image
Pipe Insulation | 2 | ORP05812 | L=6.2 ft x D=1/4 inch | 9.68 | 19.36 | Amazon | 1 month | Ordered | Buy
Pipe | 1 | EPPW2012 | L=25ft x D=1/4 inch Di = 1/8 inch | 16.6 | 16.6 | Granger | 1 Week | Ordered | Buy
Pump | 1 | 517100002 | Fountain Pump | 217 | 217 | Grainger | 3 Days | Order February | Buy
T fitting | 1 | ‎JWBTST6 | D=1/8in, Pack of 5, 3 way | 9.82 | 9.82 | Amazon | 1 Week | Ordered | Buy
Polyester Waterproof Tape | 1 | B07HCP3HXM | APT 3.5 thic polyester tape | 15.88 | 15.88 | Amazon | -------------------- | Received | Buy
Activator | 1 | B0006IUWCC | fastcap super glue adhesive | 21.19 | 21.19 | Amazon | -------------------- | Received | Buy
Super Glue | 1 | B01FWZNPUY | 20g bob smith super glue | 12.99 | 12.99 | Amazon | -------------------- | Received | Buy
Aluminum panels with channels | 4 |  | 12inx12inx5/8in | 0 | 0 | Machine Shop | 1 Week | Partially Made | Make
Aluminum backing | 4 |  | 12inx12inx.25in | 0 | 0 | Machine shop | 1 Week | Partially Made | Make
Thic Aluminum Sheet | 2 |  | 12inx12inx5/8in | 123.73 | 247.46 | Machine Shop | -------------------- | Received | Buy
Thin Aluminum Sheet | 2 | 9246K425 | 12inx48inx.25in | 165.97 | 331.94 | McMaster Carr | -------------------- | Received | Buy
Bolts | 1 | B01NBJT5OR | 1/4-20inx.5in pack:100 | 21.76 | 21.76 | McMaster Carr | Same Week | Ordered | Buy
Nuts | 1 | B07VG2569H | 1/4-20in pack:100 | 9.77 | 9.77 | McMaster Carr | Same Week | Ordered | Buy
2x4 Wood | 8 | 312528776 | 2inx4inx8ft | 3.75 | 30 | Home Depot | Same Day | Order February | Buy
5 Gallon Bucket | 2 | 05GLHD2 | 5 gal hope depot bucket | 4.98 | 9.96 | Home Depot | Same Day | Order February | Buy
Black Paint | 1 | 779402 | 1-gal | 48.48 | 48.48 | Home Depot | Same Day | Order February | Buy
White Reflective Paint | 1 |  | reflective 1-gal | 50 | 50 | Heath Paint | Same Day | Order February | Buy
Thermometer | 1 | HH804W | 2 channel RTD | 142.86 | 142.86 | Omega | 5 Weeks | Order February | Buy
Thermocouples | 6 | 5LSC-5SRTC | 32-900F range | 166.42 | 998.52 | Omega | 4 Weeks | Partial Recieved/ Partially order Feb | Buy
Flow rate sensors | 2 | BV1000-2000-3000 | .1-2.5 LPM | 83 | 166 | Omega | 5 Weeks | Order February | Buy
Valves | 1 | SV6000-Series | .25 in dia 2 Way pack of 2 | 11 | 11 | Amazon | 1 Week | Ordered | Buy
Radiation Sensor | 1 | R8008 | RT-100 | 512.1 | 512.1 | JLW Instruments | 1 Week | Order February | Buy
Copper Coil | 1 | SKU CX-9030008-WW | 60°C coolant temperature | 10.91 | 10.91 | Amazon | 1 Week | Ordered | Buy
Folding Table | 1 |  | 60 in long | 110 | 110 | Home Depot | Same Day | Order February | Buy
Storage Tote | 1 | 301356003 | 38 gal | 39.98 | 39.98 | Home Depot | Same Day | Order February | Buy
Gasket | 1 | 38R341 | 1/16 in Thick | 61.7 | 61.7 | Grainger | 3 Days | Received | Buy
NPT | 8 | 20YZ84 | 1/8 in .75 in length | 4.66 | 37.28 | Grainger | 3 Days | Partially Odered/ Partially Recieved | Buy
Mylar Film | 1 | B07WP3NKN7 | 6 pack 210cmx130cm | 10.97 | 10.97 | Amazon | Same Week | Ordered | Buy
Teflon Tape | 1 | B07F3QTDH7 | .5 in 30ft long | 0.98 | 0.98 | Home Depot | Same Day | Received | Buy
|  |  |  | Total Price: | 3164.51
|  |  | Tax & Shipping | Total Price + 20% | 3797.412
|  |  | With 5% Contingency | Final Price | 3987.2826