## Gantt Chart Template
To edit this Gantt chart template, you have to make a copy on your Drive: Go to File > Make a Copy. Manage your projects with the help of GanttPRO Gantt chart software
ME486C - HCC26 Gantt
Task name | Stard date | End date | Assigned | Status | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07
Project Management | 2026-01-12 | 2026-01-18 | ME Team | Done
Engineering Calculations | 2026-01-12 | 2026-01-23 | ME Team | Done
Individual Analysis | 2026-01-18 | 2026-01-30 | ME Team | Open
Cultural and Social Analysis | 2026-01-20 | 2026-01-30 | Dawson | In process
Site Operation Analysis | 2026-01-20 | 2026-01-30 | Karsten | Done
Prony Brake Uncertainty Analysis | 2026-01-20 | 2026-01-30 | Nathaniel | Done
Solar Power Analysis | 2026-01-20 | 2026-01-30 | Anthony | Done
33% Build | 2026-01-12 | 2026-02-03 | ME Team | Open
Engineering Model Summary | 2026-01-12 | 2026-01-18 | Corbin | Done
Final CAD and Fabrication Files | 2026-01-12 | 2026-01-20 | Corbin | Done
Manufacturing Confirmation | 2026-01-12 | 2026-01-20 | ME Team | In process
EE Architecture Development | 2026-01-12 | 2026-01-22 | EE Team | In process
Testing Plan | 2026-01-12 | 2026-01-24 | Karsten | In process
Manufacture and Fabrication | 2026-01-12 | 2026-01-24 | ME Team | In process
EE Build and Integration | 2026-01-12 | 2026-01-25 | EE Team | In process
Prototype Dry Assembly | 2026-01-12 | 2026-01-26 | ME Team | In process
Community Connections | 2026-01-12 | 2026-02-03 | Nathaniel | In process
Website Check #1 | 2026-01-12 | 2026-02-20 | Nathaniel | In process
February Competition Submissions | 2026-01-12 | 2026-02-23 | ME Team | In process
Siting Challenge | 2026-01-13 | 2026-02-23 | ME Team | In process
Design Challenge | 2026-01-14 | 2026-02-23 | ME Team | In process
Community Connections | 2026-01-15 | 2026-02-23 | ME Team | In process
67% Build | 2026-02-04 | 2026-02-26 | ME Team | Open
Validating Manufactured Components | 2026-02-04 | 2026-02-26 | ME Team | Open
Validating Subsystem Integration | 2026-02-04 | 2026-02-26 | ME Team | Open
Cost Models Refined using as-built | 2026-02-04 | 2026-02-26 | ME Team | Open
Environmental and Operational Check | 2026-02-04 | 2026-02-26 | ME Team | Open
Prony Brake Build and Test | 2026-02-04 | 2026-02-26 | ME Team | Open
Prototype Testing | 2026-02-04 | 2026-02-26 | ME Team | Open

## Assignees and Status
Assignees | Status
Karsten | Open
Anthony | In process
Nathaniel | Closed
EE Team
ME Team
Dawson | Done
Corbin