## Sheet1
Project Title: <title> | [5 empty] | Report for | <pick a week from the list>
Team Members:
| Kiwi | Chewie | Taffy | Chauncey | Member 5
XXX
Task ID | Status | Description |  |  |  | Assigned to | Start Date | Start Week | Expected End Date | Finished on Week | Measurable Outcome | Actual Outcome | XXX
1 | Done | Project preference memo |  |  |  | Chewie | 2023-09-08 | Week 4 (Sep/18 - Sep-22) | 2023-09-13 | Week 4 (Sep/18 - Sep-22) | includes all items specified in given instructions | met requirements | XXX
2 | In progress | Create team name |  |  |  | All | 2023-09-15 | Week 4 (Sep/18 - Sep-22) | 2023-09-20 |  | Name is defined |  | XXX
3 | Next up | Team standards doc - introduction |  |  |  | Taffy (50%), Chauncey (50%) | 2023-09-18 | Week 4 (Sep/18 - Sep-22) | 2023-09-22 |  | grammatically correct, introduction as specified |  | XXX
4 | [12 empty] | XXX
5 | [12 empty] | XXX
6 | [12 empty] | XXX
7 | [12 empty] | XXX
8 | [12 empty] | XXX
9 | [12 empty] | XXX
10 | [12 empty] | XXX
11 | [12 empty] | XXX
12 | [12 empty] | XXX
13 | [12 empty] | XXX
14 | [12 empty] | XXX
15 | [12 empty] | XXX
16 | [12 empty] | XXX
17 | [12 empty] | XXX
18 | [12 empty] | XXX
19 | [12 empty] | XXX
20 | [12 empty] | XXX
21 | [12 empty] | XXX
22 | [12 empty] | XXX
23 | [12 empty] | XXX
24 | [12 empty] | XXX
25 | [12 empty] | XXX
26 | [12 empty] | XXX
27 | [12 empty] | XXX
28 | [12 empty] | XXX
29 | [12 empty] | XXX
30 | [12 empty] | XXX
31 | [12 empty] | XXX
32 | [12 empty] | XXX
33 | [12 empty] | XXX
34 | [12 empty] | XXX
35 | [12 empty] | XXX
36 | [12 empty] | XXX
37 | [12 empty] | XXX
38 | [12 empty] | XXX
39 | [12 empty] | XXX
40 | [12 empty] | XXX
41 | [12 empty] | XXX
42 | [12 empty] | XXX
43 | [12 empty] | XXX
44 | [12 empty] | XXX
45 | [12 empty] | XXX
46 | [12 empty] | XXX
47 | [12 empty] | XXX
48 | [12 empty] | XXX
49 | [12 empty] | XXX
50 | [12 empty] | XXX
51 | [12 empty] | XXX
52 | [12 empty] | XXX
53 | [12 empty] | XXX
54 | [12 empty] | XXX
55 | [12 empty] | XXX
56 | [12 empty] | XXX
57 | [12 empty] | XXX
58 | [12 empty] | XXX
59 | [12 empty] | XXX
60 | [12 empty] | XXX
61 | [12 empty] | XXX
62 | [12 empty] | XXX
63 | [12 empty] | XXX
64 | [12 empty] | XXX
65 | [12 empty] | XXX
66 | [12 empty] | XXX
67 | [12 empty] | XXX
68 | [12 empty] | XXX
69 | [12 empty] | XXX
70 | [12 empty] | XXX
71 | [12 empty] | XXX
72 | [12 empty] | XXX
73 | [12 empty] | XXX
74 | [12 empty] | XXX
75 | [12 empty] | XXX
76 | [12 empty] | XXX
77 | [12 empty] | XXX
78 | [12 empty] | XXX

## Sheet2
Status | Week
<pick a status from the list> | <pick a week from the list>
Done | Week 4 (Sep/18 - Sep-22)
In progress | Week 5 (Sep/25 - Sep 29)
Overdue | Week 6 (Oct/2 - Oct 6)
Next up | Week 7 (Oct/9 - Oct-13)
Week 8 (Oct/16 - Oct/20)
Week 9 (Oct/23 - Oct/27)
Week 10 (Oct/30 - Nov/3)
Week 11 (Nov/6 - Nov/10)
Week 12 (Nov/13 - Nov-17)
Week (Nov/20 - Nov-24)
Week 14 (Nov/27 - Dec/1)
Week 15 (Dec/4 - Dec/8)
Week 16 (Dec/11 - Dec14)